SIGNATURE HONEY CRAFT COFFEE · VETERAN OWNED & OPERATED QUEZ COFFEE CO. LLC PRE-LAUNCH MASTER TIMELINE Now → Soft Open February 2027 → Grand Opening March–April 2027 Every thread. Every deadline. One document.

| KEY DATE | MILESTONE |
| --- | --- |
| Now — May 2026 | Pre-separation: VA claim, GI Bill transfer, Reserves unit confirmation, DIAL classification call |
| June 2026 | LLC formation · EIN · Business checking · Sales tax permit · SBA application begins · $10K equity deposit |
| Jul – Aug 2026 | SBA Veterans Advantage Loan application · Trailer quotes · SBDC advisor meetings · Lot agreement confirmed |
| Aug – Sep 2026 | Family relocation to Council Bluffs · ETS transition prep · Loan approval target |
| Sep – Oct 2026 | Iowa DIAL plan review submission · CFPM certifications · Insurance bound · Lot agreement signed |
| Oct – Nov 2026 | SBA loan funds disbursed (target Nov 2026) · Trailer shell purchased · Build begins |
| Nov – Dec 2026 | Trailer build · Equipment ordered and installed · Social media launch — start posting NOW |
| Dec 2026 – Jan 2027 | DIAL physical inspection · Council Bluffs vendor permit · Fire Marshal inspection · Test drinks |
| January 2027 | All licenses in hand · Full menu recipe testing · Staff trained · Soft open date confirmed |
| February 2027 | SOFT OPEN — 35th & Broadway · First cups served · Every 10th drink free begins |
| March 10, 2027 | ETS from active duty · Full civilian operations · Owner full-time on the trailer |
| March – April 2027 | GRAND OPENING · Media pitch · Community event · Social blitz · Delivery platforms activated |
| August 2027 | First SBA loan payment due ($674/mo · 9-month deferment ends) |

| CRITICAL — Gates everything downstream | HIGH — Must hit the window | ☐ Pending | ✓ Complete |
| --- | --- | --- | --- |

FULL PRE-LAUNCH TIMELINE

| DATE | CATEGORY | ACTION ITEM | DONE |
| --- | --- | --- | --- |
| NOW – MAY 2026 · Pre-Separation Actions — Do Before ETS |  |  |  |
| Now | VA / Benefits | File VA disability claim — the earlier you file, the earlier benefits begin. Do not wait until ETS. | ☐ |
| Now | VA / Benefits | File GI Bill transfer to dependents while still on active duty — cannot be done after ETS. | ☐ |
| Now | Regulatory | Call Pottawattamie County Environmental Health AND Iowa DIAL Food Plan Review (515.350.7587) — confirm mobile food unit classification for a coffee-only trailer. This call gates your entire trailer build spec. | ☐ |
| Now | Regulatory | Ask DIAL: hood type required (Type I, Type II, or exhaust fan only) for steaming milk with no open flame cooking. | ☐ |
| Now | Regulatory | Ask DIAL: minimum fresh water tank capacity and water heater rating for your unit class. | ☐ |
| Now | Research | Visit 3–5 coffee operations in Omaha / Council Bluffs. Note build details, equipment brands, service window layout. | ☐ |
| Now | Social Media | Create @QuezcoffeeIA on TikTok, Instagram, and 'Quez Coffee – Council Bluffs' on Facebook. Start posting immediately — the build is content. | ☐ |
| Now | Research | Get 3 used trailer shell quotes from dealers or private sellers. Target $8,000–$10,000 range. | ☐ |
| Now | Financial | Begin assembling SBA loan application documents: personal tax returns (2 years), pay stubs, personal financial statement (SBA Form 413), business plan. | ☐ |
| May 2026 | Military | Submit CSP (Capstone / Transition) paperwork the day TAP completes. | ☐ |
| May 2026 | Reserves | Confirm Army Reserves unit near Council Bluffs — unit assignment must be confirmed for Reserves pay and TRICARE Reserve Select to activate post-ETS. | ☐ |
| JUNE 2026 · Entity Formation & Financial Foundation |  |  |  |
| Jun 2026 | Legal | Form Quez Coffee Co. LLC in Iowa — sos.iowa.gov. Cost: ~$50. Business name must match what you want on licenses, tax accounts, and loan documents. | ☐ |
| Jun 2026 | Legal | Get EIN (Federal Employer Identification Number) — IRS.gov, free, instant online. Do this the same day you form the LLC. | ☐ |
| Jun 2026 | Financial | Open dedicated business checking account — use EIN, not SSN. Do not commingle personal and business funds from Day 1. | ☐ |
| Jun 2026 | Tax | Apply for Iowa Sales Tax Permit — Iowa Dept of Revenue, tax.iowa.gov. Free. Required before first sale. | ☐ |
| Jun 2026 | Financial | Deposit $10,000 owner equity injection into business checking account. This confirms equity for the SBA loan application. | ☐ |
| Jun 2026 | Financial | Apply for business credit card in the LLC name. Used for equipment purchases, supplies — not personal expenses. | ☐ |
| Jun 2026 | SBA Loan | Begin formal SBA Veterans Advantage Loan application with SBDC advisor. Target: application submitted by July 15. | ☐ |
| Jun 2026 | SBDC | Schedule first meeting with Iowa SBDC advisor. Bring business plan v3.0, personal financial statement, and equity confirmation. | ☐ |
| JUL – AUG 2026 · Loan Application & Location Confirmation |  |  |  |
| Jul 2026 | SBA Loan | Submit SBA Veterans Advantage Loan application — $45,000 at 6.5% / 7 years, 9-month deferment requested. Target approval by September. | ☐ |
| Jul 2026 | Location | Confirm primary soft-open lot at 35th & Broadway in writing. Signed B-01 or B-02 lot agreement on file. | ☐ |
| Jul 2026 | Research | Identify 2–3 additional rotation locations for Year 1. Initiate lot agreement conversations. | ☐ |
| Jul 2026 | Military | Submit PTDY request for September family relocation (if eligible). | ☐ |
| Jul 2026 | Regulatory | Research Iowa veteran small business grants — Iowa Economic Development Authority, IADVA, local community foundations. | ☐ |
| Aug 2026 | Relocation | Family relocation to Council Bluffs completes. House purchase closes. | ☐ |
| Aug 2026 | Financial | Rental property — issue tenant 30-day written notice of rent increase if applicable. File all landlord paperwork through proper Iowa channels. | ☐ |
| Aug 2026 | Equipment | Get final quotes on espresso machines, grinder, ice machine, refrigeration, blender, water heater. Compare NSF-certified models. | ☐ |
| SEP – OCT 2026 · Regulatory Submissions & Build Prep |  |  |  |
| Sep 2026 | Loan | SBA loan approval target. Funds targeted for November disbursement. | ☐ |
| Sep 2026 | Regulatory | Submit Iowa DIAL Food Plan Review package — floor plan, equipment schedule, plumbing/mechanical schematics, menu, SOPs. Use D-01 checklist before submission. | ☐ |
| Sep 2026 | Licensing | Apply for CFPM (Certified Food Protection Manager) certification — ServSafe Manager or Prometric. Both operators. ~$200/person. Required before physical inspection. | ☐ |
| Sep 2026 | Insurance | Get quotes for general liability insurance — $1M per occurrence minimum. Bind policy before permit inspection. | ☐ |
| Sep 2026 | Trailer | Purchase trailer shell. Document purchase with bill of sale. Photograph pre-build condition. | ☐ |
| Oct 2026 | Regulatory | DIAL plan review response — expect 3–4 weeks from submission. Address any comments immediately. Incomplete submissions restart the clock. | ☐ |
| Oct 2026 | Equipment | Order all equipment. Confirm NSF/ANSI certifications on all food-contact equipment before ordering. | ☐ |
| Oct 2026 | Legal | Confirm Iowa DIAL plan review approval before construction starts. Do not build before approval. | ☐ |
| NOV – DEC 2026 · Build, Install, & Social Launch |  |  |  |
| Nov 2026 | Financial | SBA loan funds disbursed. Deposit into business checking. Begin tracking all pre-opening expenses in QuickBooks. | ☐ |
| Nov 2026 | Build | Trailer build begins. Owner leads — licensed electrical and plumbing contractors for permit-required work only. | ☐ |
| Nov 2026 | Equipment | Equipment arrives. Photograph serial numbers. Register warranties. File manuals in I-01 Equipment Binder. | ☐ |
| Nov 2026 | Equipment | Equipment installed per Iowa DIAL-approved plans. No deviations from approved layout without re-submission. | ☐ |
| Nov 2026 | Social | TikTok: daily build documentation posts. Show every major step — wiring, plumbing, equipment install. This is your pre-launch audience. | ☐ |
| Dec 2026 | Build | Trailer build complete. Owner walk-through and self-inspection using D-01 checklist. Every Priority (P) and Priority Foundation (Pf) item must pass. | ☐ |
| Dec 2026 | Regulatory | Schedule Iowa DIAL physical inspection. Do NOT schedule until all D-01 checklist items pass. | ☐ |
| Dec 2026 | Regulatory | Council Bluffs Mobile Food Vendor Permit application submitted to CB Parks & Recreation — (712) 890-5291. Requires Iowa DIAL license first. | ☐ |
| Dec 2026 | Regulatory | Fire Marshal inspection — CB Parks & Rec triggers this after vendor permit application. Have extinguisher, generator, and LP lines ready. | ☐ |
| Dec 2026 | QuickBooks | QuickBooks Online + QuickBooks Intuit POS configured. Iowa sales tax rate 7% set. Chart of accounts established. First test transaction run. | ☐ |
| Dec 2026 | Social | TikTok/Instagram: 500+ followers target by December 31. If behind, increase posting frequency — daily minimum. | ☐ |
| JANUARY 2027 · Final Prep — 30 Days to Soft Open |  |  |  |
| Jan 2027 | Licensing | Iowa DIAL Annual Mobile Food Unit License in hand. Council Bluffs vendor permit in hand. General liability insurance COI on file. | ☐ |
| Jan 2027 | Operations | Full menu test run — all 15 drinks built to Recipe Bible spec. Both operators make every drink. Timed to build targets. | ☐ |
| Jan 2027 | Operations | Staff hired and fully trained — all 3 phases of E-03 completed. Solo clearance signed by owner for all staff. | ☐ |
| Jan 2027 | Operations | H-01 Hiring & Onboarding packet completed for each staff member. Iowa New Hire Report filed within 15 days of hire. | ☐ |
| Jan 2027 | Operations | Cold brew protocol tested — nightly brew confirmed. All house-made syrups produced and labeled. Full daily operations log run for 1 week. | ☐ |
| Jan 2027 | Equipment | Full equipment run-through at soft-open location — generator, water system, espresso machine, POS. Simulate a full 8-hour service day. | ☐ |
| Jan 2027 | Location | Lot agreement for 35th & Broadway active and signed. Access confirmed for February 1. | ☐ |
| Jan 2027 | Financial | Opening cash drawer funded. Deposit to business checking confirmed. QuickBooks POS opening count set. | ☐ |
| Jan 2027 | Social | TikTok/Instagram: 1,000+ followers target. Countdown to soft open posts begin — '14 days,' '7 days,' '3 days,' 'Tomorrow.' | ☐ |
| Jan 2027 | Loyalty | Stamp cards ordered and in hand. Stamp tool (honey bee or Q mark) ordered and tested. Card holder mounted inside trailer. | ☐ |
| Jan 2027 | Honey | Confirm honey supply from both Iowa suppliers. Minimum 2 gallons on hand for opening week. | ☐ |
| Jan 2027 | Supplies | All consumables ordered and on hand: cups (all sizes), lids, sleeves, straws, gloves, paper towels, soap, sanitizer, test strips. | ☐ |
| Jan 2027 | Media | Soft open announcement drafted: press release for Council Bluffs Nonpareil, social media posts, Facebook event created. | ☐ |
| FEBRUARY 2027 · Soft Open — No Owner Draw — Build the Rhythm |  |  |  |
| Feb 1, 2027 | OPERATIONS | SOFT OPEN DAY. 35th & Broadway. 6:00 AM. First cup served. Every 10th drink free from Day 1. | ☐ |
| Feb 2027 | Operations | Daily Operations Log (E-02) completed every single shift. Both operator initials on every log. This is an Iowa DIAL compliance document. | ☐ |
| Feb 2027 | Financial | Iowa sales tax collected 7% on every transaction. Funds go directly to sales tax sub-account — never operating funds. | ☐ |
| Feb 2027 | Financial | No owner draw in February or March. All revenue goes to operating reserves. $2,500/month draw begins April 2027. | ☐ |
| Feb 2027 | Social | Post every day. At minimum: location update + one drink or behind-the-scenes post. TikTok minimum 3x/week. | ☐ |
| Feb 2027 | Operations | Customer feedback loop — after first 30 days, conduct 10–20 customer interviews. What do they love? What would they change? Cut bottom sellers. Double down on top performers. | ☐ |
| Feb 2027 | Financial | QuickBooks weekly report every Monday. Compare cups/day against break-even (49 cups/day at $6.00 average). Know your numbers. | ☐ |
| MARCH – APRIL 2027 · Grand Opening & Owner Full-Time |  |  |  |
| Mar 10, 2027 | MILESTONE | ETS from active duty. Ryan Joseph Rodriquez is now a full-time business owner. Reserve commitment continues monthly. | ☐ |
| Mar 2027 | Grand Opening | GRAND OPENING event — full social blitz, media pitch to Nonpareil / KETV / WOWT, veteran community outreach, Facebook event. | ☐ |
| Mar 2027 | Media | Press release to: Council Bluffs Nonpareil, KETV (ABC), WOWT (NBC), Omaha World-Herald. Pitch 3–4 weeks in advance of Grand Opening date. | ☐ |
| Apr 2027 | Financial | Owner draw begins — $2,500/month. Confirm revenue supports draw before first payment. | ☐ |
| Apr 2027 | Delivery | Activate DoorDash, Uber Eats, and/or GrubHub once build times are consistently under 3 minutes. Do not activate until operations are stable. | ☐ |
| Apr 2027 | Location | Second rotation location confirmed and active. 2–3 weekly location rotations in place. | ☐ |
| Apr 2027 | Tax | Iowa sales tax Q1 return filed — due April 30, 2027. Iowa Dept of Revenue, tax.iowa.gov. | ☐ |
| POST-OPENING MILESTONES · Months 3–12 |  |  |  |
| Month 3 | Financial | Confirm Conservative scenario ($4,680/mo) is met. If Base scenario ($7,800/mo), hold draw and build reserve. | ☐ |
| Month 6 | Social | 5,000 TikTok followers target · 3,000 Instagram · 2,000 Facebook. Review G-03 playbook — adjust content strategy if behind. | ☐ |
| Month 6 | Review | 30-day customer research complete. Menu adjusted based on sales data. Bottom sellers cut or swapped for seasonal. | ☐ |
| Aug 2027 | Financial | FIRST SBA LOAN PAYMENT DUE — $674/month. Confirm payment posted. Log confirmation number. 9-month deferment ends. | ☐ |
| Q3 2027 | Tax | Iowa sales tax Q2 return filed — due July 31, 2027. | ☐ |
| Q4 2027 | Planning | Year 2 planning: second trailer quotes, additional lot agreements, S-Corp election evaluation. Consult CPA if Year 1 net profit approaches $50,000. | ☐ |
| Q4 2027 | Tax | Iowa sales tax Q3 return filed — due October 31, 2027. | ☐ |
| Jan 2028 | Annual | Iowa DIAL license renewal ($250). Council Bluffs vendor permit renewal. Insurance renewal. Annual checklist (E-02) completed. | ☐ |
| Jan 2028 | Tax | Iowa sales tax Q4 return filed — due January 31, 2028. Annual reconciliation complete. | ☐ |
| 2028 | Growth | YEAR 2 — Second trailer unit. S-Corp elected. Multi-location schedule. First full-time hire. $200,000–$250,000 revenue target. | ☐ |

QUICK REFERENCE — CRITICAL GATES

These items gate everything downstream. If any of these slip, the launch date slips. Check this list weekly.

| DEADLINE | GATE | GATES | DONE |
| --- | --- | --- | --- |
| Now (active duty) | DIAL classification call — confirms trailer build spec | Everything downstream | ☐ |
| Now (active duty) | GI Bill transfer to dependents — cannot do after ETS | Dependent education benefits forever | ☐ |
| June 2026 | LLC formed + EIN obtained | SBA application, bank account, all licenses | ☐ |
| June 2026 | $10,000 equity deposited to business checking | SBA loan approval | ☐ |
| Jul 15, 2026 | SBA loan application submitted | Loan approval timeline, Nov disbursement | ☐ |
| Aug 2026 | Lot agreement signed — 35th & Broadway | Confirmed soft-open location | ☐ |
| Sep 2026 | DIAL plan review package submitted | Physical inspection, permits, build start | ☐ |
| Sep 2026 | CFPM certification — both operators | Iowa license, legal service operations | ☐ |
| Sep 2026 | General liability insurance bound | Vendor permit, lot agreements, DIAL | ☐ |
| Oct 2026 | DIAL plan review APPROVED | Construction start — do not build before approval | ☐ |
| Nov 2026 | SBA loan funds disbursed | Equipment orders, trailer build, supplies | ☐ |
| Dec 2026 | DIAL physical inspection PASSED | Iowa DIAL Annual License | ☐ |
| Dec 2026 | CB vendor permit + Fire Marshal inspection PASSED | Legal operation in Council Bluffs | ☐ |
| Jan 2027 | All licenses in hand, staff trained, supplies on hand | February 1 soft open date | ☐ |
| Feb 1, 2027 | SOFT OPEN | Revenue, customer feedback, operations rhythm | ☐ |
| Apr 30, 2027 | Iowa sales tax Q1 return filed | Compliance — $25/day late penalty | ☐ |
| Aug 1, 2027 | First SBA loan payment — $674 | Loan in good standing | ☐ |

This timeline is a living document. When a gate is cleared, check the box. When a date slips, update the timeline and recalculate what moves with it. The soft open date of February 2027 is the anchor — work backward from it, not forward from today.